## 2016
| Version |  |  | V1 | V2 | V3
| Issued | HCL: |  | 2015-08-11
2016 Production Schedule | Revised
LCGC E-Separation Solutions (Monthly Thrice / 1st to 3rd Thursday)
Jan - June | DAYS | 2016-01-07 | 2016-01-14 | 2016-01-21 | 2016-02-04 | 2016-02-11 | 2016-02-18 | 2016-03-03 | 2016-03-10 | 2016-03-17 | 2016-04-07 | 2016-04-14 | 2016-04-21 | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-06-02 | 2016-06-09 | 2016-06-16
Ad Close | -5 | 2015-12-29 | 2016-01-07 | 2016-01-12 | 2016-01-28 | 2016-02-04 | 2016-02-10 | 2016-02-25 | 2016-03-03 | 2016-03-10 | 2016-03-31 | 2016-04-07 | 2016-04-14 | 2016-04-28 | 2016-05-05 | 2016-05-12 | 2016-05-24 | 2016-06-02 | 2016-06-09
Material due for ads to be created by Web Ops | -5 | 2015-12-29 | 2016-01-07 | 2016-01-12 | 2016-01-28 | 2016-02-04 | 2016-02-10 | 2016-02-25 | 2016-03-03 | 2016-03-10 | 2016-03-31 | 2016-04-07 | 2016-04-14 | 2016-04-28 | 2016-05-05 | 2016-05-12 | 2016-05-24 | 2016-06-02 | 2016-06-09
Final ads to Web PM (referencing date for e-news) | -4 | 2015-12-30 | 2016-01-08 | 2016-01-13 | 2016-01-29 | 2016-02-05 | 2016-02-11 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-29 | 2016-05-06 | 2016-05-13 | 2016-05-25 | 2016-06-03 | 2016-06-10
Web Ad Trafficker send Ad Tags to Web PM | -4 | 2015-12-30 | 2016-01-08 | 2016-01-13 | 2016-01-29 | 2016-02-05 | 2016-02-11 | 2016-02-26 | 2016-03-04 | 2016-03-11 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-29 | 2016-05-06 | 2016-05-13 | 2016-05-25 | 2016-06-03 | 2016-06-10
ACI Editor sends completed enewsletter instruction sheet to Web PM | -3 | 2016-01-04 | 2016-01-11 | 2016-01-14 | 2016-02-01 | 2016-02-08 | 2016-02-12 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-26 | 2016-06-06 | 2016-06-13
Web PM builds eNewsletter and sends proof link to ACI | -2 | 2016-01-05 | 2016-01-12 | 2016-01-19 | 2016-02-02 | 2016-02-09 | 2016-02-16 | 2016-03-01 | 2016-03-08 | 2016-03-15 | 2016-04-05 | 2016-04-12 | 2016-04-19 | 2016-05-03 | 2016-05-10 | 2016-05-17 | 2016-05-31 | 2016-06-07 | 2016-06-14
Corrections are made by Web PM per instructions from ACI | -2 | 2016-01-05 | 2016-01-12 | 2016-01-19 | 2016-02-02 | 2016-02-09 | 2016-02-16 | 2016-03-01 | 2016-03-08 | 2016-03-15 | 2016-04-05 | 2016-04-12 | 2016-04-19 | 2016-05-03 | 2016-05-10 | 2016-05-17 | 2016-05-31 | 2016-06-07 | 2016-06-14
Web Production Manager sends test email to ACI staff | -2 | 2016-01-05 | 2016-01-12 | 2016-01-19 | 2016-02-02 | 2016-02-09 | 2016-02-16 | 2016-03-01 | 2016-03-08 | 2016-03-15 | 2016-04-05 | 2016-04-12 | 2016-04-19 | 2016-05-03 | 2016-05-10 | 2016-05-17 | 2016-05-31 | 2016-06-07 | 2016-06-14
Corrections made by Web PM if necessary | -1 | 2016-01-06 | 2016-01-13 | 2016-01-20 | 2016-02-03 | 2016-02-10 | 2016-02-17 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-04-06 | 2016-04-13 | 2016-04-20 | 2016-05-04 | 2016-05-11 | 2016-05-18 | 2016-06-01 | 2016-06-08 | 2016-06-15
Final Approval | -1 | 2016-01-06 | 2016-01-13 | 2016-01-20 | 2016-02-03 | 2016-02-10 | 2016-02-17 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-04-06 | 2016-04-13 | 2016-04-20 | 2016-05-04 | 2016-05-11 | 2016-05-18 | 2016-06-01 | 2016-06-08 | 2016-06-15
Web PM send mailing details to emedia (SF) team | -1 | 2016-01-06 | 2016-01-13 | 2016-01-20 | 2016-02-03 | 2016-02-10 | 2016-02-17 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-04-06 | 2016-04-13 | 2016-04-20 | 2016-05-04 | 2016-05-11 | 2016-05-18 | 2016-06-01 | 2016-06-08 | 2016-06-15
Emedia (SF) team schedule the mailing | -1 | 2016-01-06 | 2016-01-13 | 2016-01-20 | 2016-02-03 | 2016-02-10 | 2016-02-17 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-04-06 | 2016-04-13 | 2016-04-20 | 2016-05-04 | 2016-05-11 | 2016-05-18 | 2016-06-01 | 2016-06-08 | 2016-06-15
E-newsletter mails | 0 | 2016-01-07 | 2016-01-14 | 2016-01-21 | 2016-02-04 | 2016-02-11 | 2016-02-18 | 2016-03-03 | 2016-03-10 | 2016-03-17 | 2016-04-07 | 2016-04-14 | 2016-04-21 | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-06-02 | 2016-06-09 | 2016-06-16
Jul - Dec | DAYS | 2016-07-07 | 2016-07-14 | 2016-07-21 | 2016-08-04 | 2016-08-11 | 2016-08-18 | 2016-09-01 | 2016-09-08 | 2016-09-15 | 2016-10-06 | 2016-10-13 | 2016-10-20 | 2016-11-03 | 2016-11-10 | 2016-11-17 | 2016-12-01 | 2016-12-08 | 2016-12-15
Ad Close | -5 | 2016-06-29 | 2016-07-07 | 2016-07-14 | 2016-07-28 | 2016-08-04 | 2016-08-10 | 2016-08-25 | 2016-08-30 | 2016-09-08 | 2016-09-29 | 2016-10-06 | 2016-10-13 | 2016-10-27 | 2016-11-03 | 2016-11-10 | 2016-11-21 | 2016-12-01 | 2016-12-08
Material due for ads to be created by Web Ops | -5 | 2016-06-29 | 2016-07-07 | 2016-07-14 | 2016-07-28 | 2016-08-04 | 2016-08-10 | 2016-08-25 | 2016-08-30 | 2016-09-08 | 2016-09-29 | 2016-10-06 | 2016-10-13 | 2016-10-27 | 2016-11-03 | 2016-11-10 | 2016-11-21 | 2016-12-01 | 2016-12-08
Final ads to Web PM (referencing date for e-news) | -4 | 2016-06-30 | 2016-07-08 | 2016-07-15 | 2016-07-29 | 2016-08-05 | 2016-08-11 | 2016-08-26 | 2016-08-31 | 2016-09-09 | 2016-09-30 | 2016-10-07 | 2016-10-14 | 2016-10-28 | 2016-11-04 | 2016-11-11 | 2016-11-22 | 2016-12-02 | 2016-12-09
Web Ad Trafficker send Ad Tags to Web PM | -4 | 2016-06-30 | 2016-07-08 | 2016-07-15 | 2016-07-29 | 2016-08-05 | 2016-08-11 | 2016-08-26 | 2016-08-31 | 2016-09-09 | 2016-09-30 | 2016-10-07 | 2016-10-14 | 2016-10-28 | 2016-11-04 | 2016-11-11 | 2016-11-22 | 2016-12-02 | 2016-12-09
ACI Editor sends completed enewsletter instruction sheet to Web PM | -3 | 2016-07-01 | 2016-07-11 | 2016-07-18 | 2016-08-01 | 2016-08-08 | 2016-08-12 | 2016-08-29 | 2016-09-01 | 2016-09-12 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-28 | 2016-12-05 | 2016-12-12
Web PM builds eNewsletter and sends proof link to ACI | -2 | 2016-07-05 | 2016-07-12 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 2016-08-16 | 2016-08-30 | 2016-09-06 | 2016-09-13 | 2016-10-04 | 2016-10-11 | 2016-10-18 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-29 | 2016-12-06 | 2016-12-13
Corrections are made by Web PM per instructions from ACI | -2 | 2016-07-05 | 2016-07-12 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 2016-08-16 | 2016-08-30 | 2016-09-06 | 2016-09-13 | 2016-10-04 | 2016-10-11 | 2016-10-18 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-29 | 2016-12-06 | 2016-12-13
Web Production Manager sends test email to ACI staff | -2 | 2016-07-05 | 2016-07-12 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 2016-08-16 | 2016-08-30 | 2016-09-06 | 2016-09-13 | 2016-10-04 | 2016-10-11 | 2016-10-18 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-29 | 2016-12-06 | 2016-12-13
Corrections made by Web PM if necessary | -1 | 2016-07-06 | 2016-07-13 | 2016-07-20 | 2016-08-03 | 2016-08-10 | 2016-08-17 | 2016-08-31 | 2016-09-07 | 2016-09-14 | 2016-10-05 | 2016-10-12 | 2016-10-19 | 2016-11-02 | 2016-11-09 | 2016-11-16 | 2016-11-30 | 2016-12-07 | 2016-12-14
Final Approval | -1 | 2016-07-06 | 2016-07-13 | 2016-07-20 | 2016-08-03 | 2016-08-10 | 2016-08-17 | 2016-08-31 | 2016-09-07 | 2016-09-14 | 2016-10-05 | 2016-10-12 | 2016-10-19 | 2016-11-02 | 2016-11-09 | 2016-11-16 | 2016-11-30 | 2016-12-07 | 2016-12-14
Web PM send mailing details to emedia (SF) team | -1 | 2016-07-06 | 2016-07-13 | 2016-07-20 | 2016-08-03 | 2016-08-10 | 2016-08-17 | 2016-08-31 | 2016-09-07 | 2016-09-14 | 2016-10-05 | 2016-10-12 | 2016-10-19 | 2016-11-02 | 2016-11-09 | 2016-11-16 | 2016-11-30 | 2016-12-07 | 2016-12-14
Emedia (SF) team schedule the mailing | -1 | 2016-07-06 | 2016-07-13 | 2016-07-20 | 2016-08-03 | 2016-08-10 | 2016-08-17 | 2016-08-31 | 2016-09-07 | 2016-09-14 | 2016-10-05 | 2016-10-12 | 2016-10-19 | 2016-11-02 | 2016-11-09 | 2016-11-16 | 2016-11-30 | 2016-12-07 | 2016-12-14
E-newsletter mails | 0 | 2016-07-07 | 2016-07-14 | 2016-07-21 | 2016-08-04 | 2016-08-11 | 2016-08-18 | 2016-09-01 | 2016-09-08 | 2016-09-15 | 2016-10-06 | 2016-10-13 | 2016-10-20 | 2016-11-03 | 2016-11-10 | 2016-11-17 | 2016-12-01 | 2016-12-08 | 2016-12-15
Distribution List
ACI: Francis Heid, Keith Hammerbeck, Carrie Landman
Melissa Feiro, Megan L'Heureux, Stephen A. Brown, Cindy Delonas, Stephanie
Sarah Darcy, Michael J. Tessalone, Edward Fantuzzi, Laura Bush, Anne Lavigne
Shaffer, Christine Shappell, Jerry Xenos, Elizabeth Thomas, Elizabeth McClean, Gareth Pickering
HCL: ENL.AdvanstarSupport@mpe.hcl.com, lyrisapproval@media.advanstar.com
Holiday Note:
01/01 Issue moved to 01/02
2013-12-24
2013-12-25
2013-12-31
2014-01-01
2014-01-26
2014-02-17
2014-05-01
2014-05-26
2014-08-15
2014-10-02
2014-10-23
2014-11-28
2014-12-25
2014-07-04
2014-09-01
2014-11-27
2014-12-24

## holidays
List of Holidays
2015-11-26 | Thursday | thanksgiving
2015-11-27 | Friday | thanksgiving
2015-12-24 | Thursday | Christmas
2015-12-25 | Friday | Christmas
2015-12-31 | Thursday | New Years
2016-01-01 | Friday | New Years
2016-01-15 | Friday | Pongal (India)
2016-01-18 | Monday | Martin Luther King Day
2016-01-26 | Tuesday | Republic Day (India)
2016-02-15 | Monday | Presidents Day
| Saturday | RRD - Li
2016-05-27 | Friday | Friday before Memorial Day, leave early
2016-05-30 | Monday | Memorial Day
2016-07-04 | Monday | Independence Day
2016-08-15 | Monday | Independence Day (India)
2016-09-02 | Friday | Friday before Labor Day, leave early
2016-09-05 | Monday | Labor Day
2016-11-23 | Wednesday | Thanksgiving, leave early
2016-11-24 | Thursday | thanksgiving
2016-11-25 | Friday | thanksgiving
2016-12-23 | Friday | RRD - Christmas
2016-12-26 | Monday | Christmas
2016-12-30 | Friday | New Years
Saturday
Saturday
UK Holiday
2016-01-01 | New year
2016-03-25 | Good Friday
2016-03-28 | Easter Monday
2016-05-02 | Early May Bank Holdiay
2016-05-30 | May Bank Holiday
2016-08-29 | Summber Bank Holiday
2016-12-26 | Boxing day
2016-12-27 | Christmas day
2016-01-15 | Friday | Pongal (India)
2016-01-26 | Tuesday | Republic Day (India)
2016-08-15 | Monday | Independence Day (India)

## Mail date WeekdayValidation
Mail Date | Week Day | Week Day Validation |  |  |  |  | Holiday Validation
2016-01-07 | Thursday | No Error | 42376 | 2015-11-26 | 42334 | #N/A | #N/A
2016-01-14 | Thursday | No Error | 42383 | 2015-11-27 | 42335 | #N/A | #N/A
2016-01-21 | Thursday | No Error | 42390 | 2015-12-24 | 42362 | #N/A | #N/A
2016-02-04 | Thursday | No Error | 42404 | 2015-12-25 | 42363 | #N/A | #N/A
2016-02-11 | Thursday | No Error | 42411 | 2015-12-31 | 42369 | #N/A | #N/A
2016-02-18 | Thursday | No Error | 42418 | 2016-01-01 | 42370 | #N/A | #N/A
2016-03-03 | Thursday | No Error | 42432 | 2016-01-15 | 42384 | #N/A | #N/A
2016-03-10 | Thursday | No Error | 42439 | 2016-01-18 | 42387 | #N/A | #N/A
2016-03-17 | Thursday | No Error | 42446 | 2016-01-26 | 42395 | #N/A | #N/A
2016-04-07 | Thursday | No Error | 42467 | 2016-02-15 | 42415 | #N/A | #N/A
2016-04-14 | Thursday | No Error | 42474 | 2016-05-27 | 42517 | #N/A | #N/A
2016-04-21 | Thursday | No Error | 42481 | 2016-05-30 | 42520 | #N/A | #N/A
2016-05-05 | Thursday | No Error | 42495 | 2016-07-04 | 42555 | #N/A | #N/A
2016-05-12 | Thursday | No Error | 42502 | 2016-08-15 | 42597 | #N/A | #N/A
2016-05-19 | Thursday | No Error | 42509 | 2016-09-02 | 42615 | #N/A | #N/A
2016-06-02 | Thursday | No Error | 42523 | 2016-09-05 | 42618 | #N/A | #N/A
2016-06-09 | Thursday | No Error | 42530 | 2016-11-23 | 42697 | #N/A | #N/A
2016-06-16 | Thursday | No Error | 42537 | 2016-11-24 | 42698 | #N/A | #N/A
|  |  |  | 2016-11-25 | 42699
|  |  |  | 2016-12-23 | 42727
|  |  |  | 2016-12-26 | 42730
|  |  |  | 2016-12-30 | 42734